# Customs Clearance Platform (India) – Day-Wise Implementation Plan

Version: 1.0

Scope: Phase -1 (Architecture & Engineering Preparation) and Phase 0 (Platform Foundation)

Jurisdiction: India (ICEGATE / ITC-HS, GST, Customs Duty, Cess)

Team model: Solo delivery — the user acts as human-in-the-loop / decision-maker and implementer, with Claude providing design, code, review, and documentation support. No separate DB/backend/API/frontend teams; one person moves through all layers sequentially per module.

# How to Read This Plan

Each entry is one working day. Days assume focused solo work with AI pairing — no cross-team handoff delays, but still gated: a day's output should be reviewed/accepted before moving to the next.

"Deliverable" is the concrete artifact you should have in hand at day's end — use it to self-check progress.

If a day runs over, don't compress the next day — slip the whole plan by the same amount. The sequence matters more than the calendar date.

This plan covers Phase -1 and Phase 0 only (per agreed scope). Phase 1 onward (Enterprise Core, India tariff/reference data sourcing, Core Customs Processing) will get its own day-wise plan once we approach it — flagged as a reminder at the end of this document.

A "Multi-Agent?" column has been added to every table. It flags whether that day's work is a candidate for parallel subagent execution (multiple independent sub-tasks worked simultaneously to shorten elapsed time) instead of straight sequential solo work. See the summary section below before Week 1.

# Multi-Agent Parallelization — Summary & Recommendation

Multiple subagents can work in parallel only where sub-tasks are genuinely independent of each other's output. Forcing parallelism onto sequential/dependent work (e.g. schema before evaluation pipeline) creates conflicting drafts that cost more time to reconcile than they save. Recommendation: use parallel agents only on the days flagged "Yes" below; keep everything else sequential.

| Legend | Meaning |
| --- | --- |
| Yes | Sub-tasks are independent — recommended candidate for parallel subagents |
| Partial | Some parts can run in parallel, but a review/merge step still needs to happen sequentially |
| No | Has a real dependency chain or requires one coherent decision-maker — keep sequential |

Days 2–3: Core-entity model vs. Rules/Charges model can be drafted in parallel, then merged on Day 4's review (Partial — merge is sequential).

Days 16–18: logging-lib, security-lib, persistence-lib, messaging-lib, audit-lib have no interdependencies at build time — strong candidate to compress 3 days into parallel agent runs (Yes).

Days 26–29 (observability): logging rollout, metrics, tracing, and alerting touch overlapping config but can largely be scaffolded in parallel and wired together on Day 30's review (Partial).

Days 36–37: Configuration service and Notification service are independent builds (Yes).

Days 41–44 (hardening): security review, performance baseline, CI/CD hardening, and documentation are independent workstreams over the same completed codebase (Yes).

Rules-engine days (31–34), infra bring-up (21–25), and all "review/sign-off" days are explicitly marked No — they either have a strict build order or require your single decision as human-in-the-loop.

# Phase -1: Architecture & Engineering Preparation (Days 1–20, ~4 weeks)

Goal: everything that must be decided once, before writing production code, so later phases don't require rework.

## Week 1 (Days 1–5): Domain Model & Bounded Contexts

| Day | Focus | Tasks | Deliverable | Multi-Agent? |
| --- | --- | --- | --- | --- |
| 1 | Kickoff & Domain Scoping | Re-confirm MVP scope from PRD for India; list bounded contexts (Shipment, Declaration, Commodity, Party, Permit, Charges, Segregation/Rules); identify which are in v1 vs later | Bounded-context map (1-page diagram + notes) | No — single scoping decision |
| 2 | Canonical Data Model – Core Entities | Draft entity attributes for Shipment, Declaration, Commodity, Party (from PRD Ch.2, 4, 6, 7), adapted for India (ITC-HS 8-digit, GST/Cess fields) | Draft ER diagram v0.1 | Partial — can run alongside Day 3 |
| 3 | Canonical Data Model – Rules & Charges | Draft entity model for Charges, Permits, Shipment Indicators, and the Rules/Segregation model (rule, condition, priority, decision trace) | ER diagram v0.2 including rules entities | Partial — can run alongside Day 2 |
| 4 | Data Model Review & Refinement | Walk through end-to-end scenario (e.g. informal import from China to India) against the model; fix gaps | ER diagram v1.0 (signed off) | No — merge/review needs one owner |
| 5 | Bounded Context Interfaces | Define how contexts talk to each other (events vs direct calls); list domain events (ShipmentValidated, HSClassified, DeclarationSubmitted, etc.) | Context map + domain event catalog v1.0 | No — depends on Day 4 model |

## Week 2 (Days 6–10): API & Coding Standards

| Day | Focus | Tasks | Deliverable | Multi-Agent? |
| --- | --- | --- | --- | --- |
| 6 | API Standards | Define REST conventions: URL structure, versioning, pagination, filtering, error format, correlation ID header | API standards doc v1.0 | No — single standards decision |
| 7 | OpenAPI Contract Skeletons | Draft OpenAPI stubs for Shipment and Declaration services (paths + schemas, no implementation) | openapi/shipment.yaml, openapi/declaration.yaml (draft) | Yes — one stub per service in parallel |
| 8 | Coding Standards & ADR Template | Choose backend stack/framework, set naming/style conventions, create ADR template; write ADR-001 (stack choice), ADR-002 (rules-engine approach: config-driven vs code) | Coding standards doc + ADR-001, ADR-002 | No — needs one coherent decision |
| 9 | Repository & Branching Strategy | Set up repo structure (mono-repo vs multi-repo decision), branching model, commit conventions, PR/review checklist (even solo, use PR-to-self discipline for traceability) | Repo initialized with structure + CONTRIBUTING.md | No — single structural decision |
| 10 | Security & Audit Standards | Define auth approach (JWT/OAuth2), field-level audit logging pattern, data-at-rest/in-transit encryption approach | Security standards doc v1.0 | No — single standards decision |

## Week 3 (Days 11–15): CI/CD & Quality Gates

| Day | Focus | Tasks | Deliverable | Multi-Agent? |
| --- | --- | --- | --- | --- |
| 11 | CI Pipeline Setup | Set up build pipeline (GitHub Actions/Azure DevOps): build, lint, unit test stages | CI pipeline green on empty scaffold project | No — foundational, others build on it |
| 12 | Code Scanning & Coverage Gates | Integrate static analysis (SonarQube/equivalent) and coverage reporting; set thresholds (95% core logic / 80% CRUD per v2 plan) | CI pipeline enforcing coverage + lint gates | No — depends on Day 11 pipeline |
| 13 | CD Pipeline & Environments | Set up deployment pipeline to a dev environment (containerized); define environment promotion path (dev → staging → prod) | Automated deploy to dev environment working | No — depends on Day 11 pipeline |
| 14 | Test Automation Scaffolding | Set up unit test framework, integration test framework, Postman/Newman or equivalent for API contract tests | Test scaffolding with one passing sample test per layer | Partial — unit vs API test scaffolds can be split |
| 15 | Quality Gate Checklists | Formalize Gate 1–5 checklists (Architecture, Backend, API, Frontend, Release) as living checklists to use at each phase exit | Quality gate checklist doc (checkable, reusable) | Yes — one checklist per gate in parallel |

## Week 4 (Days 16–20): Platform Libraries & Rules-Engine Spike

Days 16–18 are the strongest parallelization candidate in Phase -1: logging-lib, security-lib, persistence-lib, messaging-lib, and audit-lib have no build-time interdependencies. Recommendation: run these as parallel subagent tasks and compress 3 days into roughly 1, using the freed time as buffer or to start the Day 19 design spike early.

| Day | Focus | Tasks | Deliverable | Multi-Agent? |
| --- | --- | --- | --- | --- |
| 16 | Reusable Library – Logging & Error Handling | Build shared logging module (structured logs, correlation ID propagation) and standard exception/error-response handling | logging-lib, error-handling-lib (versioned packages) | Yes — independent of Day 17/18 libs |
| 17 | Reusable Library – Security & Auditing | Build shared auth middleware and generic audit-trail module (event type, old/new value, user, timestamp, correlation ID) per PRD audit requirements | security-lib, audit-lib | Yes — independent of Day 16/18 libs |
| 18 | Reusable Library – Persistence & Messaging | Build shared repository base classes / ORM setup, and event-bus publish/subscribe wrapper | persistence-lib, messaging-lib | Yes — independent of Day 16/17 libs |
| 19 | Rules-Engine Design Spike | Design (not build) the configurable rules engine: rule schema (condition, priority, action), storage model, versioning, decision-trace output — per PRD Ch.5 segregation logic, scoped for India rules (e.g. De Minimis threshold, FTZ, controlled goods) | Rules-engine design doc + schema (ready for Phase 0 build) | No — single coherent design |
| 20 | Phase -1 Exit Review | Walk through Gate 1 (Architecture Review) checklist against everything built; fix gaps; confirm readiness to start Phase 0 | Phase -1 sign-off note; go/no-go decision | No — you are the sole reviewer/approver |

# Phase 0: Platform Foundation (Days 21–50, ~6 weeks)

Goal: the technical base every later module builds on — infra, identity, security, observability, and a working (empty) rules-engine skeleton.

## Week 5 (Days 21–25): Core Infrastructure

| Day | Focus | Tasks | Deliverable | Multi-Agent? |
| --- | --- | --- | --- | --- |
| 21 | Environment & Containerization | Set up local/dev Kubernetes (or Docker Compose for solo-scale dev) and base service template project | Running "hello world" service in a container | No — everything else builds on this |
| 22 | API Gateway | Stand up API Gateway (routing, rate limiting, basic auth passthrough) | Gateway routes hello-world service | No — depends on Day 21 |
| 23 | Identity & Access | Implement Identity service (or integrate managed identity provider); user/role model per PRD personas (Broker, Supervisor, Compliance Officer, Admin) | Working login + role-based token issuance | No — depends on Day 21/22 |
| 24 | Event Bus | Stand up event bus (Kafka/RabbitMQ/Azure Service Bus); publish/consume a test domain event | Event bus operational with sample event flow | Partial — infra bring-up independent of Day 23, but same environment |
| 25 | Base Security Framework | Wire security-lib into gateway and identity; enforce authenticated routes end-to-end | Auth-protected sample endpoint working | No — depends on Day 22/23 |

## Week 6 (Days 26–30): Observability

Days 26–29 can largely be scaffolded in parallel (each touches a different tool/pipeline), with Day 30 as the mandatory sequential wiring/review step.

| Day | Focus | Tasks | Deliverable | Multi-Agent? |
| --- | --- | --- | --- | --- |
| 26 | Structured Logging Rollout | Wire logging-lib into all scaffold services; centralize log output | Centralized log view (e.g. ELK/Loki) showing service logs | Partial — parallel with 27–29, merge on Day 30 |
| 27 | Monitoring & Metrics | Set up metrics collection (Prometheus/equivalent) and a basic dashboard (Grafana) | Dashboard showing service health/latency | Partial — parallel with 26, 28, 29 |
| 28 | Distributed Tracing | Add correlation-ID-based tracing across gateway → service → event bus | Trace visible for one end-to-end sample request | Partial — parallel with 26, 27, 29 |
| 29 | Alerting Basics | Configure basic alerts (service down, error rate spike) | At least one working alert rule | Partial — parallel with 26–28 |
| 30 | Observability Review | Validate logs, metrics, traces, alerts all correlate for one sample request/event | Observability sign-off note | No — single reviewer, ties everything together |

## Week 7 (Days 31–35): Rules Engine Skeleton

This week is deliberately marked No throughout — schema, evaluation pipeline, versioning, and admin API form a strict build chain; parallelizing here would produce mismatched schema/service assumptions.

| Day | Focus | Tasks | Deliverable | Multi-Agent? |
| --- | --- | --- | --- | --- |
| 31 | Rules Engine – Storage Model | Implement DB schema for rules (from Phase -1 design spike): rule, condition, priority, action, version | Rules storage schema migrated | No — everything else depends on this schema |
| 32 | Rules Engine – Evaluation Pipeline | Implement rule evaluation service (input facts → matched rules → ordered by priority → outcome) | Evaluation service passes unit tests on dummy rules | No — depends on Day 31 schema |
| 33 | Rules Engine – Versioning & Decision Trace | Implement rule versioning and decision-trace capture (per PRD Ch.5 explainability requirement) | Decision trace visible for a test rule evaluation | No — depends on Day 32 pipeline |
| 34 | Rules Engine – Admin API (minimal) | Expose minimal API to create/update/deactivate a rule (no UI yet — Postman/Swagger only) | CRUD API for rules, testable via Swagger | No — depends on Day 31–33 |
| 35 | Rules Engine Review | Load 2–3 real India-specific sample rules (e.g. De Minimis value threshold, controlled-goods flag) and verify evaluation + trace output | Rules engine validated against real India business rules | No — single validation pass |

## Week 8 (Days 36–40): Configuration & Notification Base

| Day | Focus | Tasks | Deliverable | Multi-Agent? |
| --- | --- | --- | --- | --- |
| 36 | Configuration Service | Build central configuration service (feature flags, business parameters like currency, thresholds) — no redeploy needed for changes | Config service live, one value changed without redeploy | Yes — independent of Day 37 notification build |
| 37 | Notification Base | Build basic notification service (email/in-app event-driven notification skeleton) | Sample notification fires on a test event | Yes — independent of Day 36 config build |
| 38 | Audit Trail End-to-End | Wire audit-lib into a real sample flow (e.g. config change) to confirm full audit capture per PRD requirements | Audit record visible with old/new value, user, timestamp | No — depends on Day 36 config service existing |
| 39 | Seed Data & Reference Tables | Load initial India reference data stubs: country codes, currency (INR + majors), unit-of-measure list (placeholder ahead of full tariff sourcing in Phase 1) | Reference/lookup tables seeded | Yes — independent data-entry task, can run alongside Day 36/37 |
| 40 | Integration Smoke Test | End-to-end smoke test: auth → gateway → sample service → rules engine → audit → notification | All foundation pieces verified working together | No — single end-to-end verification pass |

## Week 9 (Days 41–45): Hardening & Documentation

Days 41–44 are independent workstreams over the same already-completed codebase — a strong parallelization candidate, potentially compressing 4 days into roughly 2.

| Day | Focus | Tasks | Deliverable | Multi-Agent? |
| --- | --- | --- | --- | --- |
| 41 | Security Hardening | Review auth flows, secrets management, encryption at rest/in transit against Phase -1 security standards | Security checklist passed | Yes — independent of Days 42–44 |
| 42 | Performance Baseline | Run basic load test against gateway + sample service to establish a performance baseline | Baseline performance report | Yes — independent of Days 41, 43, 44 |
| 43 | CI/CD Hardening | Ensure CI/CD pipeline enforces all quality gates automatically (coverage, lint, security scan) before merge | Pipeline blocks a deliberately broken PR | Yes — independent of Days 41, 42, 44 |
| 44 | Documentation Pass | Document Phase 0 architecture (diagrams, runbooks: how to run locally, how to deploy, how to add a new service) | Phase 0 runbook + architecture doc | Yes — independent of Days 41–43 |
| 45 | Buffer / Catch-up Day | Reserved for slippage from Weeks 5–8; if unused, get ahead on Phase 1 India tariff-sourcing research | Plan back on schedule | No — reserved slack, not parallel work |

## Week 10 (Days 46–50): Phase 0 Exit

| Day | Focus | Tasks | Deliverable | Multi-Agent? |
| --- | --- | --- | --- | --- |
| 46 | Gate 1 Re-check (Architecture) | Re-verify standards, naming, security, performance, documentation across everything built in Phase 0 | Gate 1 checklist passed | No — you are the sole approver |
| 47 | Gate 2 Dry Run (Backend) | Verify business-rule validation, unit test coverage, static analysis, security scan on foundation services | Gate 2 checklist passed | No — you are the sole approver |
| 48 | Regression Pass | Re-run full smoke/integration suite from Day 40 to confirm nothing regressed during hardening | All foundation tests green | No — single verification pass |
| 49 | Phase 1 Kickoff Prep | Prepare Phase 1 entry: confirm scope (User Mgmt, Organization, Notification, Audit, Configuration UI-facing pieces) and India tariff-sourcing plan inputs | Phase 1 kickoff brief drafted | No — planning/decision task |
| 50 | Phase 0 Sign-off | Formal go/no-go review; document lessons learned; confirm readiness to proceed to Phase 1 | Phase 0 sign-off note | No — you are the sole approver |

# Reminder Flags Embedded in This Plan

Day 39: only placeholder reference data is loaded. Full India tariff master (ITC-HS) sourcing and licensing is a Phase 1 workstream — do not assume tariff data is production-ready at this point.

Target customs authority (e.g. ICEGATE) is still unconfirmed — flagged previously, and relevant again once Phase 8 (Integration) planning approaches. No action needed yet.

# What Comes Next

This document intentionally stops at the end of Phase 0 (Day 50). Once we complete Phase 0, we will prepare a fresh day-wise plan for Phase 1 (Enterprise Core + India tariff/reference data sourcing) and Phase 2/3 (Master Data + Core Customs Processing for India), so that later-phase detail reflects what we actually learn while building Phase -1 and Phase 0 — rather than being locked in now based on assumptions.