# Customs Clearance Platform – Phase-wise Development Plan

Version: 2.0

Document Type: Phase-wise Development Plan (Revised)

Change Basis: Incorporates review feedback on the v1 plan — see "Revision Summary" below.

# Revision Summary (v1 → v2)

This version addresses five issues raised in review of v1:

Segregation/Rules Engine skeleton moved earlier (into Phase 0/1) instead of waiting until Phase 4/5, since nearly every downstream module (Declaration, Duty, Compliance) depends on rule-driven behavior from day one.

Tariff & HS Code data sourcing is now called out as its own explicit workstream starting in Phase 1, given the scale (multi-jurisdiction, versioned, millions of records) and external licensing dependency (WCO HS, country-specific extensions).

The 95% unit test coverage gate is now explicitly scoped to core business/rules logic (duty, tariff, declaration, segregation) rather than applied as a blanket rule across all backend services, including CRUD-heavy master data modules.

Customs gateway certification/sandbox access is flagged as an external dependency and risk in Phase 8, with schedule buffer, since it is gated by government agencies rather than engineering velocity.

Team topology and parallelism are now made explicit — phases are grouped into overlapping tracks rather than presented as a strictly serial sequence.

# 1. Delivery Approach

The platform (comparable in scope to CargoWise, Descartes, SAP GTS, Oracle GTM) will be developed architecture-first and backend-first, with every phase passing defined exit criteria before the next begins. A 5-level delivery hierarchy is used:

Platform Program

Phase

Business Domain

Layer

Sprint / Feature

## 1.1 Development Layering (per phase)

Each phase is completed in four sequential layers; no frontend work begins until backend layers pass their quality gates.

| Layer | Scope | Exit Criteria |
| --- | --- | --- |
| 1 – Database | Tables, indexes, views, constraints, seed data, migration scripts | 100% schema validation, referential integrity, performance baseline |
| 2 – Backend Services | Entities, repositories, domain models, business services, rules, transactions | ≥95% unit test coverage for core business/rules logic; static analysis clean |
| 3 – Business APIs | REST APIs, OpenAPI/Swagger, auth, pagination, filtering, versioning | Contract tests passed, integration tests green, API docs finalized |
| 4 – User Interface | Angular/React/Blazor UI consuming completed, stable APIs | UI functional tests, accessibility review, UX sign-off |

Note (v2 change): the 95% coverage target applies specifically to core business/rules logic — segregation, duty/tax, tariff, declaration lifecycle. Master-data CRUD services carry a lower, still-enforced coverage bar (target 80%) so the gate reflects risk rather than being applied uniformly.

# 2. Revised Phase Roadmap

Phases are grouped into four overlapping delivery tracks rather than one strictly serial chain. Tracks 2 and 3 may run in parallel once Track 1 foundations are stable, with dedicated teams per track.

| Track | Phases | Can Run in Parallel With |
| --- | --- | --- |
| Track 1 – Foundation | Phase -1, Phase 0, Phase 1 | N/A (must complete first) |
| Track 2 – Core Domain | Phase 2 (Master Data), Phase 3 (Core Customs), Phase 4 (Compliance) | Track 3 |
| Track 3 – Operational Platform | Phase 5 (Workflow), Phase 6 (Finance), Phase 7 (Documents) | Track 2 |
| Track 4 – Outward-Facing | Phase 8 (Integration), Phase 9 (Reporting), Phase 10 (Customer Experience) | Begins once Track 2/3 core APIs stabilize |

## 2.1 Phase -1: Architecture & Engineering Preparation (New — 6–10 weeks)

Inserted before Phase 0 per review feedback. Reduces rework and ensures cross-team consistency before any production code is written.

Finalize domain-driven design and bounded contexts

Define the canonical data model

Establish API standards and OpenAPI contracts

Establish coding standards and Architecture Decision Records (ADRs)

Set up CI/CD, quality gates, code scanning, and test automation

Build reusable platform libraries: logging, error handling, security, auditing, messaging, persistence

Create developer templates and reference implementations

(v2 addition) Produce an initial rules-engine design spike — schema for storing configurable rules (segregation, duty applicability) — so Phase 0/1 can build against it rather than hard-coding early logic that gets rewritten in Phase 4/5

## 2.2 Phase 0: Platform Foundation

Architecture, CI/CD, Kubernetes, Identity, Logging, Monitoring, API Gateway, Event Bus, Security base framework

(v2 addition) Rules Engine skeleton: rule storage, versioning, and evaluation pipeline (empty of business rules, but structurally ready) — so Phase 3 does not have to retrofit configuration-driven behavior later

No business modules yet.

## 2.3 Phase 1: Enterprise Core

User Management, Organization, Security, Notification, Audit, Configuration

(v2 addition) Tariff & Reference Data Sourcing workstream kicks off here in parallel: licensing and ingestion planning for WCO HS, country-specific tariff extensions (ASEAN AHTN, US HTS, EU TARIC, etc.), exchange rate feeds, and lookup table sourcing — this is called out explicitly because Chapter 8 of the PRD treats tariff data as foundational, and sourcing/licensing lead time is an external dependency that can otherwise block Phase 2/3 unnoticed

Sequence: Backend first, then Testing, then UI.

## 2.4 Phase 2: Master Data Platform

Modules: Customers, Products, HS Codes, Countries, Ports, Carriers

Tariff Master ingestion (multi-jurisdiction, versioned) continues here, consuming the sourcing work started in Phase 1

Sequence: Backend → Services → API → UI.

## 2.5 Phase 3: Core Customs Processing

Modules: Shipment, Declaration, Duty, Tariff, Permit, Customs Submission

(v2 addition) Segregation Engine business rules are authored and activated here against the rules-engine skeleton built in Phase 0 — avoiding rework of Phase 3 logic once Phase 4 compliance rules land

Sequence: Backend → Services → API → UI.

## 2.6 Phase 4: Compliance Platform

Modules: Screening, Risk, OGA, Holds, Inspections

Runs in parallel with the latter part of Phase 3 (Track 2), since compliance rules extend the same rules-engine foundation rather than introducing a new one.

## 2.7 Phase 5: Workflow Platform

Modules: Workflow, Tasks, SLA, Escalation, Collaboration

## 2.8 Phase 6: Financial Platform

Modules: Billing, Duty, Tax, Payments

## 2.9 Phase 7: Document Platform

Modules: DMS, OCR, Templates, Digital Signature

## 2.10 Phase 8: Integration Platform

Modules: API Gateway, Adapters, Events, EDI, Customs Gateways

(v2 addition) Risk flag: Customs Gateway certification and sandbox access are controlled by external government agencies, not engineering velocity. This phase carries a schedule buffer and should begin agency sandbox/certification requests as early as Phase 3, since approval lead times often run in parallel tracks independent of development readiness.

## 2.11 Phase 9: Reporting Platform

Modules: Dashboards, BI, KPIs, Analytics, AI

## 2.12 Phase 10: Customer Experience

Customer Portal, Mobile App, Broker UI, Executive Dashboard

Developed last, once all APIs and backend capabilities are stable — UI teams focus on experience rather than waiting on backend changes.

# 3. Quality Gates

| Stage | Exit Criteria |
| --- | --- |
| Database | Schema review passed, migrations validated, performance baseline achieved, integrity checks passed |
| Backend | ≥95% unit test coverage for core business/rules logic (≥80% for master-data CRUD services), static code analysis clean, business rule validation complete |
| API | Contract tests passed, integration tests green, authentication/authorization verified, API documentation finalized |
| Frontend | UI functional tests passed, accessibility review completed, responsive behavior verified, UX sign-off |
| System | End-to-end workflows validated, regression suite passed, performance/load tests completed, security testing passed |
| Production | UAT sign-off, operational runbooks approved, deployment rehearsed, rollback plan validated |

## 3.1 Phase Exit Gates

| Gate | Checklist |
| --- | --- |
| Gate 1 – Architecture Review | Standards followed, naming conventions, security, performance, documentation |
| Gate 2 – Backend Review | Business rules, unit tests, code coverage, static analysis (e.g. SonarQube), security scan |
| Gate 3 – API Review | Swagger/OpenAPI, API contracts, versioning, authentication, integration tests |
| Gate 4 – Frontend Review | UX, accessibility, performance, responsive design |
| Gate 5 – Release Review | SIT, UAT, regression, load test, DR test, security test |

# 4. Program Timeline (Revised, Illustrative)

| Stage | Duration | Notes |
| --- | --- | --- |
| Phase -1: Architecture & Engineering Prep | 6–10 weeks | Includes rules-engine design spike (v2 addition) |
| Phase 0: Platform Foundation | 3–4 months | Includes rules-engine skeleton (v2 addition) |
| Phase 1: Enterprise Core + Tariff Sourcing kickoff | 4–6 months | Tariff/reference data licensing started in parallel (v2 addition) |
| Phase 2–3: Master Data & Core Customs Processing | 6–8 months | Segregation rules authored against existing engine skeleton |
| Phase 4–5: Compliance & Workflow | 5–6 months | Runs partly in parallel with late Phase 3 (Track 2/3 overlap) |
| Phase 6–7: Finance & Documents | 4–5 months | Track 3, overlaps Track 2 where feasible |
| Phase 8: Integration & Customs Gateways | 4–5 months + buffer | Agency sandbox/certification requests initiated in Phase 3 (v2 addition); buffer added for external approval lead time |
| Phase 9: Reporting & Analytics | Overlaps Phase 8 | Track 4 |
| Phase 10: Customer Experience & Final Hardening | 3–4 months | Begins once Track 2/3 APIs are stable |

Overall: approximately 24–36 months for an MVP-to-enterprise platform, consistent with v1. The revisions in v2 do not change the headline duration; they front-load engine and data-sourcing risk into earlier phases and add explicit schedule buffer around externally-gated dependencies (customs agency certification), so the timeline is more defensible rather than longer.

# 5. Open Items for Sign-off

Confirm team topology: are Track 2 and Track 3 to be staffed as separate teams, or does one team rotate across tracks?

Confirm which countries/jurisdictions are in scope for MVP tariff sourcing (drives Phase 1 licensing lead time).

Confirm target customs authorities for Phase 8 sandbox access requests, so certification requests can be initiated as early as Phase 3.